## Tasks
Phase | # | Subject | Type | Project | UiPath Product | Skill (specialist) | Blocked By | Assignee | Status | SDD Reference
1. Infra & Setup | P1-1 | Provision Data Fabric entities: CallRecord (29 fields), CallFollowup (16 fields), AiUsage (8 fields, singleton-row pattern) | Infra | shared | Data Fabric | uipath-data-fabric |  |  | Done | solution-sdd.md §4
| P1-2 | Provision Orchestrator Storage Bucket cc-transcripts-incoming + daily ingestion Time Trigger | Infra | shared | Orchestrator (Storage Bucket + Triggers) | uipath-platform |  |  | Not Started | solution-sdd.md §4; orchestration-sdd.md §6
| P1-3 | Provision UiPath LLM Gateway connection | Infra | shared | LLM Gateway | uipath-platform |  |  | Not Started | solution-sdd.md §4; ai-agent-sdd.md §6
| P1-4 | Register all 4 projects into the .uipx solution (uip solution init + project add) and wire dependency bindings | Infra | solution | Orchestrator (.uipx Solution) | uipath-solution | P1-1, P1-2, P1-3 |  | Not Started | solution-sdd.md §6; solution.json
2. Deterministic — Flow | P2-01 | TriggerNewTranscript: configure storage-bucket file-created trigger (fallback: daily 06:00 Time Trigger) | Deterministic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P1-2 |  | Not Started | orchestration-sdd.md §3, §6
| P2-02 | IngestTranscript node: read file from bucket, define output contract {metadata, dialogue_text, file_name}, parsing handoff stub to Agent | Deterministic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P2-01 |  | Not Started | orchestration-sdd.md §3
| P2-03 | AIParallelFork gateway scaffold: 7-branch fan-out structure (branches wired to AI tool calls in Phase 3) | Deterministic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P2-02 |  | Not Started | orchestration-sdd.md §2-§3 (GW_AIParallelFork)
| P2-04 | AIParallelJoin gateway: wait-for-all-7 join configuration, aggregate into aiResults variable | Deterministic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P2-03 |  | Not Started | orchestration-sdd.md §2-§3 (GW_AIParallelJoin)
| P2-05 | StoreCallRecord node: Data Fabric write, map all 29 CallRecord fields, enforce single-atomic-insert rule | Deterministic | call-center-orchestration | Maestro Flow + Data Fabric | uipath-maestro-flow | P1-1, P2-04 |  | Not Started | orchestration-sdd.md §3 (Task_StoreCallRecord)
| P2-06 | SeedFollowups node: Data Fabric write, up to 3 CallFollowup rows, dedup-on-existing-seed logic | Deterministic | call-center-orchestration | Maestro Flow + Data Fabric | uipath-maestro-flow | P2-05 |  | Not Started | orchestration-sdd.md §3 (Task_SeedFollowups)
| P2-07 | HasFollowupsGateway: exclusive gateway, branch on '≥1 non-null followup_item' | Deterministic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P2-06 |  | Not Started | orchestration-sdd.md §3 (GW_HasFollowups)
| P2-08 | StartFollowupProcess node: fire-and-forget connector call to call-center-followup-case, no-wait semantics | Deterministic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P2-07 |  | Not Started | orchestration-sdd.md §3, §7
| P2-09 | DashboardRefresh marker node: converge has-followups / no-followups paths before analytics fan-out | Deterministic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P2-08 |  | Not Started | orchestration-sdd.md §3 (Task_UpdateDashboard)
| P2-10 | AnalyticsFork/AnalyticsJoin gateway scaffold: 6-branch fan-out structure (branches wired to analytics tool calls in Phase 3) | Deterministic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P2-09 |  | Not Started | orchestration-sdd.md §2-§3 (GW_AnalyticsFork/Join)
| P2-12 | Flow variables: declare transcriptFile, parsedTranscript, aiResults, callId, followupItems, hasFollowups, analyticsResults | Deterministic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P2-02 |  | Not Started | orchestration-sdd.md §4
| P2-13 | Error handling: corrupt-transcript dead-letter routing, Data Fabric write-conflict handling, StartFollowupProcess handoff-failure handling | Deterministic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P2-02, P2-05, P2-08 |  | Not Started | orchestration-sdd.md §8
| P2-14 | Project packaging files: project.uiproj, entry-points.json, operate.json, bindings_v2.json, package-descriptor.json | Deterministic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P2-01 |  | Not Started | orchestration-sdd.md §9
2. Deterministic — BPMN | P2-15 | Define lanes: Supervisor, Assigned Staff | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P1-1 |  | Not Started | followup-case-sdd.md §2
| P2-16 | StartFollowupProcess entry point (receiving side): start condition, per-CallRecord instance scoping | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P2-15 |  | Not Started | followup-case-sdd.md §6
| P2-17 | Task_SupervisorReview: BPMN task definition, CallFollowup/CallRecord read bindings for review context | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P2-16 |  | Not Started | followup-case-sdd.md §2, §4
| P2-18 | GW_ApproveReject: exclusive gateway, route approve vs reject | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P2-17 |  | Not Started | followup-case-sdd.md §3
| P2-19 | Task_RejectFollowup: terminal path, set status=rejected, preserve for audit exclusion | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P2-18 |  | Not Started | followup-case-sdd.md §3
| P2-20 | Task_AssignDetails: capture priority/assigned_to/due_date, write CallFollowup, transition to in_progress | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P2-18 |  | Not Started | followup-case-sdd.md §2-§4
| P2-21 | Task_TrackProgress: assigned-staff acknowledgement of in_progress item | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P2-20 |  | Not Started | followup-case-sdd.md §2
| P2-22 | GW_ProgressStatus: complete? gateway, loop-back semantics if still active | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P2-21 |  | Not Started | followup-case-sdd.md §3
| P2-23 | Task_MarkCompleted: terminal path, capture completion_notes, set status=completed | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P2-22 |  | Not Started | followup-case-sdd.md §2
| P2-24 | Guard rule enforcement: reject direct pending → in_progress transition (must pass through approved) | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P2-18, P2-20 |  | Not Started | followup-case-sdd.md §3
| P2-25 | HITL form: Supervisor Review (approve/reject with call context) | Deterministic | call-center-followup-case | Action Center (HITL Forms) | uipath-human-in-the-loop | P2-17 |  | Not Started | followup-case-sdd.md §5
| P2-26 | HITL form: Assign Details (priority/owner/due date) | Deterministic | call-center-followup-case | Action Center (HITL Forms) | uipath-human-in-the-loop | P2-20 |  | Not Started | followup-case-sdd.md §5
| P2-27 | HITL form: Track Progress (acknowledge in-progress) | Deterministic | call-center-followup-case | Action Center (HITL Forms) | uipath-human-in-the-loop | P2-21 |  | Not Started | followup-case-sdd.md §5
| P2-28 | HITL form: Mark Completed (free-text completion note) | Deterministic | call-center-followup-case | Action Center (HITL Forms) | uipath-human-in-the-loop | P2-23 |  | Not Started | followup-case-sdd.md §5
| P2-29 | Error handling: 48h unassigned Supervisor Review escalation to fallback approver [SME REVIEW] | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P2-17 |  | Not Started | followup-case-sdd.md §8
| P2-30 | Project packaging files: project.uiproj, entry-points.json, operate.json, bindings_v2.json, package-descriptor.json, .bpmn file | Deterministic | call-center-followup-case | Maestro BPMN (Process Orchestration) | uipath-maestro-bpmn | P2-15 |  | Not Started | followup-case-sdd.md §9
2. Deterministic — Dashboard | P2-31 | Dashboard Core Shell: routing, layout, theming, FilterContext, login wrapper (UiPath Identity) | Deterministic | call-center-dashboard | Coded Apps | uipath-coded-apps | P1-1 |  | Not Started | dashboard-sdd.md §2, §4-§5
| P2-32 | KPI & Analytics Pages (12): Dashboard, Call Log/Detail, Agents, Sentiment, Escalations, Compliance, Resolution, Intents, Trigger Words, Friction, Marketing — Data Fabric reads only | Deterministic | call-center-dashboard | Coded Apps + Data Fabric | uipath-coded-apps | P2-31 |  | Not Started | dashboard-sdd.md §3
| P2-33 | Follow-up Management Pages: /followups, /followups/overview, embed call-center-followup-case HITL forms | Deterministic | call-center-dashboard | Coded Apps + Action Center (HITL Forms) | uipath-coded-apps | P2-31, P2-25, P2-26, P2-27, P2-28 |  | Not Started | dashboard-sdd.md §3, §7, §9
2. Deterministic — Test | P2-34 | Test deterministic features: ingestion/persistence happy + error paths (Flow), full approve-assign-track-complete + reject lifecycle incl. guard rule (BPMN), dashboard data-shape contracts | Deterministic | multiple | Maestro Flow / Maestro BPMN / Coded Apps | uipath-maestro-flow / uipath-maestro-bpmn / uipath-coded-apps | P2-01..P2-33 |  | Not Started | orchestration-sdd.md §10; followup-case-sdd.md §10; dashboard-sdd.md §11
3. Agentic — Agent | P3-1 | AI Extraction Tools (7): extract_sentiment, classify_intents, detect_trigger_words, check_compliance, generate_followups, determine_resolution_flags, generate_summary | Agentic | call-center-ai-agent | Coded Agent + LLM Gateway | uipath-agents | P1-1, P1-3 |  | Not Started | ai-agent-sdd.md §3
| P3-2 | AI Analytics Tools (6): sentiment, escalation, compliance, resolution, intent, friction analytics modules | Agentic | call-center-ai-agent | Coded Agent + LLM Gateway | uipath-agents | P3-1 |  | Not Started | ai-agent-sdd.md §3
| P3-3 | Grounded Q&A tool: ask() + live 6-query aggregation context snapshot, AiUsage upsert logic. Called only by call-center-dashboard — not by the Flow. | Agentic | call-center-ai-agent | Coded Agent + LLM Gateway + Data Fabric | uipath-agents | P3-2 |  | Not Started | ai-agent-sdd.md §4, §9
3. Agentic — Flow | P3-04 | ExtractSentiment connector node: wire AIParallelFork branch 1 to Agent.extract_sentiment | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-03, P3-1 |  | Not Started | orchestration-sdd.md §3 (Task_ExtractSentiment)
| P3-05 | ClassifyIntents connector node: wire AIParallelFork branch 2 to Agent.classify_intents | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-03, P3-1 |  | Not Started | orchestration-sdd.md §3 (Task_ClassifyIntents)
| P3-06 | DetectTriggerWords connector node: wire AIParallelFork branch 3 to Agent.detect_trigger_words | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-03, P3-1 |  | Not Started | orchestration-sdd.md §3 (Task_DetectTriggerWords)
| P3-07 | CheckCompliance connector node: wire AIParallelFork branch 4 to Agent.check_compliance | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-03, P3-1 |  | Not Started | orchestration-sdd.md §3 (Task_CheckCompliance)
| P3-08 | GenFollowups connector node: wire AIParallelFork branch 5 to Agent.generate_followups | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-03, P3-1 |  | Not Started | orchestration-sdd.md §3 (Task_GenFollowups)
| P3-09 | DetermineResolution connector node: wire AIParallelFork branch 6 to Agent.determine_resolution_flags | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-03, P3-1 |  | Not Started | orchestration-sdd.md §3 (Task_DetermineResolution)
| P3-10 | GenSummary connector node: wire AIParallelFork branch 7 to Agent.generate_summary | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-03, P3-1 |  | Not Started | orchestration-sdd.md §3 (Task_GenSummary)
| P3-11 | AIParallelJoin activation: verify all 7 branches populate aiResults before StoreCallRecord proceeds | Agentic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P3-04, P3-05, P3-06, P3-07, P3-08, P3-09, P3-10, P2-04 |  | Not Started | orchestration-sdd.md §3 (GW_AIParallelJoin)
| P3-12 | SentimentAnalytics connector node: wire AnalyticsFork branch 1 to Agent.sentiment_analytics | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-10, P3-2 |  | Not Started | orchestration-sdd.md §3 (Task_SentimentAnalytics)
| P3-13 | EscalationAnalytics connector node: wire AnalyticsFork branch 2 to Agent.escalation_analytics | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-10, P3-2 |  | Not Started | orchestration-sdd.md §3 (Task_EscalationAnalytics)
| P3-14 | ComplianceAnalytics connector node: wire AnalyticsFork branch 3 to Agent.compliance_analytics | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-10, P3-2 |  | Not Started | orchestration-sdd.md §3 (Task_ComplianceAnalytics)
| P3-15 | ResolutionAnalytics connector node: wire AnalyticsFork branch 4 to Agent.resolution_analytics | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-10, P3-2 |  | Not Started | orchestration-sdd.md §3 (Task_ResolutionAnalytics)
| P3-16 | IntentAnalytics connector node: wire AnalyticsFork branch 5 to Agent.intent_analytics | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-10, P3-2 |  | Not Started | orchestration-sdd.md §3 (Task_IntentAnalytics)
| P3-17 | FrictionAnalytics connector node: wire AnalyticsFork branch 6 to Agent.friction_analytics | Agentic | call-center-orchestration | Maestro Flow + Coded Agent | uipath-maestro-flow | P2-10, P3-2 |  | Not Started | orchestration-sdd.md §3 (Task_FrictionAnalytics)
| P3-18 | AnalyticsJoin activation: verify all 6 branches populate analyticsResults before pipeline completion (non-fatal partial-result policy) | Agentic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P3-12, P3-13, P3-14, P3-15, P3-16, P3-17 |  | Not Started | orchestration-sdd.md §3, §8 (GW_AnalyticsJoin)
| P3-20 | End event wiring + full pipeline trace validation (Trigger → ... → AnalyticsJoin → End). Q&A is not wired here — see P3-21. | Agentic | call-center-orchestration | Maestro Flow | uipath-maestro-flow | P3-18 |  | Not Started | orchestration-sdd.md §2 (End_Complete)
3. Agentic — Dashboard | P3-21 | Dashboard AI Insights Page: chat UI, direct Agent.ask call (the only caller of this tool — bypasses the Flow entirely), AiUsageBadge | Agentic | call-center-dashboard | Coded Apps + Coded Agent | uipath-coded-apps | P3-3, P2-31 |  | Not Started | dashboard-sdd.md §3, §7
3. Agentic — Test | P3-22 | Test agentic features: extraction field-domain checks, analytics correctness, Q&A groundedness, full pipeline run (AI fork/join through End) | Agentic | multiple | Coded Agent / Maestro Flow / Coded Apps | uipath-agents / uipath-maestro-flow / uipath-coded-apps | P3-1..P3-21 |  | Not Started | ai-agent-sdd.md §10; orchestration-sdd.md §10
4. Packaging & Deploy | P4-1 | Package & deploy .uipx Solution: resources refresh, pack, publish/deploy to Cloud Orchestrator Acme/CallCenterAnalytics | Packaging | solution | Orchestrator (.uipx Solution) | uipath-solution | P2-34, P3-22 |  | Not Started | solution-sdd.md §6

## Legend
Phase / Color Key
Phase | Meaning
1. Infra & Setup | Shared resources: Data Fabric, Storage Bucket, Trigger, LLM Gateway, .uipx registration
2. Deterministic — Flow | Maestro Flow nodes with no AI call (trigger, persistence, gateways, error handling)
2. Deterministic — BPMN | Maestro BPMN follow-up process: lanes, tasks, gateways, HITL forms
2. Deterministic — Dashboard | Coded App pages reading Data Fabric only, no AI call
2. Deterministic — Test | Testing for all non-AI features
3. Agentic — Agent | Coded Agent tools (extraction, analytics, Q&A)
3. Agentic — Flow | Maestro Flow connector nodes that call the Coded Agent
3. Agentic — Dashboard | Coded App pages/features that call the Coded Agent directly
3. Agentic — Test | Testing for all AI-bearing features
4. Packaging & Deploy | .uipx pack/publish/deploy
Note: P2-11 (QueryAI entry point) and P3-19 (GenerateAIResponse) were removed — redundant with the Coded App calling Agent.ask() directly. See orchestration-sdd.md v1.3.